## Title Page
Group Number: |  | 4
Group Name: |  | Schedule Wizards
Group Members:
#1: | Shawn Kiruba
#2: | Adam Dauda
#3: | Ian York
#4: | Stephen Zargo
#5: | Nguyen Pham

## Product Backlog(To-do)
Group Number | 4
Project Name: | Niner connect
Description: | Ability to share scehdules in a social media format for users to connect with friends and fellow students with similar schedules. | PRODUCT BACKLOG (TO-DO)
Team Members | Shawn Kiruba, Adam Dauda, Ian York, Stephen Zargo, Nguyen Pham
Story # | Card Front | Card Back | Sprint Number | Priority | Assigned To | Comments | Estimated Points | Estimated Hours | Estimated Velocity | Actual Velocity
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality> | Sprint 1 | [5 empty] | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours)
ST - 1 | As a UNCC student, I need to be able to use my UNCC credentials so that I can use the website. | Logged into web site | Sprint 1 | 1st | Stephen |  | 1 | 1 | 1 | #REF!
ST - 2 | As a UNCC student, I want to be able to search by courses, so that I can search for a match. | Searching on an entered search term categorized by courses, returns results reflecting the search term(s) | Sprint 1 | 3rd | Shawn |  | 3 | 2 | 1.5 | #REF!
ST - 3 | As a UNCC student, I want to input my class schedule into the app, including course names, times, and locations, so I can find other students with similar schedules. | Searching for peers using class schedules and course to find other students to study with | Sprint 1 | 5th | Ian |  | 5 | 4 | 1.25 | #REF!
ST - 4 | As a UNCC student, I want to be able to chat with the student I am matched with, so we can meet up and study. | Implement a working chat bar | Sprint 1 | 2nd | Adam |  | 5 | 4 | 1.25 | #REF!
ST - 5 | As a Moderator and a UNCC student, I want the website to load quickly, so I don't waste time. | Less than 5 second load time between pages | Sprint 1 | 11th | Nguyen |  | 3 | 2 | 1.5 | #REF!
ST - 6 | As a Moderator, I want the site to contain majority of the courses taught in UNCC | Implement a course catalog | Sprint 2 | 7th | Adam |  | 3 | 2 | 1.5 | #REF!
ST - 7 | As a Moderator, I want our website database to be secure, so that the users passwords are safe. | Site encryption, SSO, is enabled. | Sprint 2 | 4th | Stephen |  | 3 | 2 | 1.5 | #REF!
ST - 8 | As a UNCC student I would like to implement a system where i can post stuff for other people to like and comment | Implement a forum system for student interaction | Sprint 2 | 6th | Shawn |  | 8 | 6 | 1.3333 | #REF!
ST - 9 | As a UNCC student, I would like the layout to be clean, so that I can easily navigate it. | User friendly application | Sprint 2 | 10th | Ian |  | 1 | 1 | 1 | #REF!
ST - 10 | As a UNCC student, I would like to be able to create an account, so I can save my preferences. | Profile page implemented | Sprint 2 | 9th | Nguyen |  | 3 | 2 | 1.5 | #REF!
ST - 11 | As a UNCC student, i would like to be able to follow other students | Impliment a follow feature | Sprint 3 | 8th | Shawn |  | 5 | 4 | 1.25 | #REF!

## DOING
Group Number | 4
Project Name: | Niner connect
Description: | Ability to share scehdules in a social media format for users to connect with friends and fellow students with similar schedules. |  |  | DOING
Team Members | Shawn Kiruba, Adam Dauda, Ian York, Stephen Zargo, Nguyen Pham
Story # | Card Front | Card Back | Estimated Points | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Sprint Number | Priority | Assigned To | Comments
ST - 1 | [5 empty] | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours) | Sprint 1
ST - 1 | Creating user stories to plan and schedule what needs to get done during each sprint |  | 1 | 1 |  | 1 | #DIV/0! | Sprint 1 | 1st | Adam, Shawn
ST - 2 | Creating low fidelity diagram and the context diagram for our created user stories |  | 1 | 1 |  | 1 | #DIV/0! | Sprint 1 | 2nd | Ian, Stephen, Nguyen
ST - 4
ST - 5
ST - 6
ST - 7
ST - 8
ST - 9
ST - 10
ST - 11
ST - 12

## DONE
Group Number | 4
Project Name: | Niner connect
Description: | Ability to share scehdules in a social media format for users to connect with friends and fellow students with similar schedules. |  |  | DONE
Team Members | Shawn Kiruba, Adam Dauda, Ian York, Stephen Zargo, Nguyen Pham |  |  |  |  | Sprint 1 |  |  |  | Sprint 2
Story # | Card Front | Card Back | Sprint Number | Priority* | Estimated Points | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Assigned To | Comments
| As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality> | [5 empty] | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours) |  |  | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours)
ST - 1
ST - 2
ST - 3
ST - 4
ST - 5
ST - 6
ST - 7
ST - 8
ST - 9
ST - 10
ST - 11
ST - 12

## Story Point Key
Story Point Key