## Title Page
Group Number: | 4
Group Name: | Schedule Wizards
Group Members:
#1: | Shawn Kiruba
#2: | Adam Dauda
#3: | Ian York
#4: | Stephen Zargo
#5: | Nguyen Pham

## Product Backlog(To-do)
Group Number | 4
Project Name: | Niner connect
Description: | Ability to share scehdules in a social media format for users to connect with friends and fellow students with similar schedules. |  | PRODUCT BACKLOG (TO-DO)
Team Members | Shawn Kiruba, Adam Dauda, Ian York, Stephen Zargo, Nguyen Pham
Story # | Card Front | Card Back | Sprint Number | Priority | Assigned To | Comments | Estimated Points | Estimated Hours | Estimated Velocity | Actual Velocity
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality> | [6 empty] | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours)

## DOING
Group Number | 4
Project Name: | Niner connect
Description: | Ability to share scehdules in a social media format for users to connect with friends and fellow students with similar schedules. |  |  | DOING
Team Members | Shawn Kiruba, Adam Dauda, Ian York, Stephen Zargo, Nguyen Pham
Story # | Card Front | Card Back | Estimated Points | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Sprint Number | Priority | Assigned To | Comments
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality> |  |  |  | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours)

## DONE
Group Number | 4
Project Name: | Niner connect
Description: | Ability to share scehdules in a social media format for users to connect with friends and fellow students with similar schedules. |  |  | DONE
Team Members | Shawn Kiruba, Adam Dauda, Ian York, Stephen Zargo, Nguyen Pham |  |  |  |  | Sprint 1 |  |  |  | Sprint 2 | [5 empty] | Sprint 3
Story # | Card Front | Card Back | Sprint Number | Priority* | Estimated Points | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Assigned To | Comments | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Assigned To | Comments
ST - 0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality> | [5 empty] | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours) |  |  | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours) |  |  |  |  | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours)
ST - 1 | Creating user stories to plan and schedule what needs to get done during each sprint |  | Sprint 1 | 12th | 1 | 1 | 1 | 1 | 1
ST - 2 | Creating low fidelity diagram and the context diagram for our created user stories |  | Sprint 1 | 13th | 1 | 1 | 1 | 1 | 1
ST - 3 | Creating UML diagram and some activity diagrams for progression on main project |  | Sprint 2 | 14th | 1 |  |  |  |  | 1 | 1 | 1 | 1 | Ian, Nguyen
ST - 4 | As a UNCC student, I need to be able to use my UNCC credentials so that I can use the website. | Logged into web site | Sprint 2 | 1st | 1 |  |  |  |  | 1 | 1 | 1 | 1 | Stephen
ST - 5 | As a UNCC student, I want to be able to search by courses, so that I can search for a match. | Searching on an entered search term categorized by courses, returns results reflecting the search term(s) | Sprint 2 | 3rd | 3 |  |  |  |  | 2 | 2 | 1.5 | 1.5 | Shawn
ST - 6 | As a UNCC student, I want to input my class schedule into the app, including course names, times, and locations, so I can find other students with similar schedules. | Searching for peers using class schedules and course to find other students to study with | Sprint 2 | 5th | 5 |  |  |  |  | 4 | 4 | 1.25 | 1.25 | Ian
ST - 7 | As a UNCC student, I want to be able to chat with the student I am matched with, so we can meet up and study. | Implement a working chat bar | Sprint 2 | 2nd | 3 |  |  |  |  | 2 | 2 | 1.5 | 1.5 | Adam
ST - 8 | As a Moderator and a UNCC student, I want the website to load quickly, so I don't waste time. | Less than 5 second load time between pages | Sprint 2 | 11th | 1 |  |  |  |  | 1 | 2 | 1 | 0.5 | Nguyen
ST - 9 | As a Moderator I want to create models for my pages so that I can store the user data efficiently. | The user should be able to store their personal information easily through the web application | Sprint 3 | 7th | 3 | [10 empty] | 2 | 1 | 1.5 | 1.5 | Adam, Stephen
ST - 10 | As a Moderator I want to create a flask based foundation to increase efficieny with the front and back end. | With this functionality, the user should be able to efficiently store data and smoothly through the flask framework | Sprint 3 | 4th | 3 | [10 empty] | 2 | 2 | 1.5 | 1.5 | Stephen, Nguyen
ST - 11 | As a Moderator I want to create a application where I can create efficient routes between pagesd | With this functionality, the user should be able to go between pages within the web application with ease | Sprint 3 | 6th | 3 | [10 empty] | 2 | 2 | 1.5 | 1.5 | Shawn, Ian, Adam
ST - 12 | As a UNCC student, I need to be able to find people with similar classes rather than exact dates and times of classes. | The user should be able to find other users that have similar classes instead of searching for them through the times of the courses. | Sprint 3 | 10th | 1 | [10 empty] | 1 | 2 | 1 | 1 | Ian
ST - 13 | As a UNCC student, I would like to create the courses for my account, while also searching for them through the classes I'm enrolled in. | The user should be able to create courses for their accounts and search for it through what the classes they are enrolled in. | Sprint 3 | 9th | 3 | [10 empty] | 2 | 2 | 1.5 | 1.5 | Nguyen, Shawn

## Story Point Key
Story Point Key